## Sheet1
[17 empty] | Milestone 1 Checklist | Status
[6 empty] | Team Members | [9 empty] | Instructions: Fill in only green portions. For the activities table put number 1 in the square under each name if that individual participated in that activity. The number of hours for each individual will be calculated automatically. Readjust cell size to be sure all text is visible as needed. | List 6 Oppurtunity Statements | In-Progress
[17 empty] | Evaluation of OS | Not started
[6 empty] | First Name | Last Name | Nickname (max 6 characters) | [8 empty] | Ranking | Not started
[6 empty] | Alexa | De Villa | Alexa | [8 empty] | Mission Statment | Not started
[6 empty] | Julia | Kyrychuk | Julia | [8 empty] | Team Blog | Not started
[6 empty] | Rayan | Ouazine | Rayan | [8 empty] | Expectation of Originality Form | Completed
[6 empty] | Arun | Thangadurai | Arun
[6 empty] | Martin | Miskovski | Martin
Add more rows as necessary
Activities Table
Date | Who |  |  |  |  | Type of Activty | Number of hourse spent | Purpose | Output | Hours spent
| Alexa | Julia | Rayan | Arun | Martin |  |  |  |  | Alexa | Julia | Rayan | Arun | Martin
Milestone 1
2026-09-12 | 1 | 1 | 1 | 1 | 1 | Work at home | 3 | Think of opportunities | Came up with 5 possible project ideas | 1 | 1 | 1 | 1 | 1
2019-01-20 | 1 | 1 | 1 | 1 | 1 | meeting | 2 | Set mission statement | 3 opportunity statements. Rank. Write mission statement | 2 | 2 | 2 | 2 | 2
[9 empty] | Total hours | 3 | 3 | 3 | 3 | 3
[9 empty] | Total team hours | [5 empty] | 15
Milestone 2
2019-01-25 | 1 |  |  |  |  | work at home | 3 | Create draft interview script | Draft interview script | 3 | 0 | 0 | 0 | 0
[9 empty] | Total hours | 3 | 0 | 0 | 0 | 0
[9 empty] | Total team hours | [5 empty] | 3
Sprint 1
2019-01-25 | 1 | 1 | 1 | 1 | 1 | Meet | 3 | Plan sprint 1 | Sprint 1 goal. Sprint backlog | 3 | 3 | 3 | 3 | 3
[9 empty] | Total hours | 3 | 3 | 3 | 3 | 3
[9 empty] | Total team hours | [5 empty] | 15
Sprint 2
2019-01-25 |  | 1 |  |  |  | Work in lab | 5 | Integrate motion sensor into project | Sensor data makes its way to serer and then to phone | 0 | 5 | 0 | 0 | 0
[9 empty] | Total hours | 0 | 5 | 0 | 0 | 0
[9 empty] | Total Team hours | [5 empty] | 5
Sprint 3
2019-01-25 | 1 | 1 | 1 | 1 | 1 | Prepare final demo | 2 | List all functionality to be demoed: What order to demo it? How to best demo each function? | Final Demo 10 minutes long | 2 | 2 | 2 | 2 | 2
[9 empty] | Total hours | 2 | 2 | 2 | 2 | 2
[9 empty] | total team hours | [5 empty] | 10
[9 empty] | Total hour over project | 11 | 13 | 8 | 8 | 8
[9 empty] | Total team hours over project | [5 empty] | 48